## Freedom Center SOV
SUBCONTRACTOR'S APPLICATION FOR PAYMENT
Continuation Sheet
APPLICATION NO: 1
APPLICATION DATE: 2/23/09
PERIOD TO: 2/28/09
HENDRICK JOB NO: 09-0999
A | B | C | D | E | F | G |  | H | I
|  |  | WORK COMPLETED |  | MATERIALS | TOTAL
ITEM | DESCRIPTION OF WORK | SCHEDULED | FROM PREVIOUS |  | PRESENTLY | COMPLETED |  | BALANCE
NO. |  | VALUE | APPLICATION | THIS PERIOD | STORED | AND STORED | % | TO | RETAINAGE
|  |  | (D+E) |  | (NOT IN | TO DATE | (G/C) | FINISH | (IF VARIABLE
[5 empty] | D OR E) | (D+E+F) |  | (C-G) | RATE)
[5 empty] | Value of |  | Formula |  | Formula
|  | No line item | Amount you have | Amount you | materials stored |  | Column G | Column C | Column G times
| Show breakdown of material | should exceed | billed previously | are billing this | on site (not in | Total of | divided by | minus | retainage rate
| and labor | 15000 | (by line) | period (by line) | work completed) | columns D,E,F | column C | column G | in contract
1 | Shop Drawings | 2000 | 0 | 2000 |  | 2000 | 100% | 0 | 100
2 | Plumbing - Material | 10000 | 0 | 1000 |  | 1000 | 10% | 9000 | 50
3 | Plumbing - Labor | 5000 | 0 | 500 |  | 500 | 10% | 4500 | 25
4 | Natural Gas - Material | 5000 | 0 | 500 |  | 500 | 10% | 4500 | 25
5 | Natural Gas - Labor | 2500 | 0 | 250 |  | 250 | 10% | 2250 | 12.5
6 | Plumbing Fixtures - Material | 10000 | 0 | 7000 |  | 7000 | 70% | 3000 | 350
7 | Plumbing Fixtures - Labor | 5000 | 0 | 3500 |  | 3500 | 70% | 1500 | 175
8 | Plumbing Equipment - Material | 4000 | 0 | 800 |  | 800 | 20% | 3200 | 40
9 | Plumbing Equipment - Labor | 2000 | 0 | 400 |  | 400 | 20% | 1600 | 20
10 | Plumbing Demolition - Material | 3000 | 0 | 1500 |  | 1500 | 50% | 1500 | 75
11 | Plumbing Demolition - Labor | 1000 | 0 | 500 |  | 500 | 50% | 500 | 25
12 | Mechanical Piping - Material | 15000 | 0 | 0 |  | 0 | 0% | 15000 | 0
13 | Mechanical Piping - Labor | 5000 | 0 | 0 |  | 0 | 0% | 5000 | 0
14 | Ductwork - Material | 7000 | 0 | 0 |  | 0 | 0% | 7000 | 0
15 | Ductwork - Labor | 2500 | 0 | 0 |  | 0 | 0% | 2500 | 0
16 | Unit Heater - Material | 2000 | 0 | 0 |  | 0 | 0% | 2000 | 0
17 | Unit Heater - Labor | 1000 | 0 | 0 |  | 0 | 0% | 1000 | 0
18 | Fans - Material | 8000 | 0 | 0 |  | 0 | 0% | 8000 | 0
19 | Fans - Labor | 2000 | 0 | 0 |  | 0 | 0% | 2000 | 0
20 | Controls | 10000 | 0 | 0 |  | 0 | 0% | 10000 | 0
21 | Test & Balance | 4000 | 0 | 0 |  | 0 | 0% | 4000 | 0
22 | Change Order #1 - Bond Fee | 2000 | 0 | 2000 |  | 2000 | 100% | 0 | 100
23 | Change Order #2 - Misc | 5000 | 0 | 0 |  | 0 | 0% | 5000 | 0
Total of this column
should equal your
contract amount
| Totals of each column | 113000 | 0 | 19950 | 0 | 19950 |  | 93050 | 997.5