## Sheet1
SAMPLE
SUBCONTRACTOR'S APPLICATION FOR PAYMENT
(Developed as a guide by The Associated General Contractors of America, The National Electrical Contractors Association, The Mechanical Contractors Association of America, The Sheet Metal and Air Conditioning Contractors National Association, etc.)
TO: | Hendrick Construction, Inc.
FROM: | (YOUR COMPANY NAME)
JOB NO: | (JOB NAME AND NUMBER)
PAYMENT REQUEST NO.: | (PAY APPLICATION NUMBER)
PERIOD: | (DATE YOU ARE BILLING THROUGH)
STATEMENT OF CONTRACT ACCOUNT:
1. Original Contract Amount | [5 empty] | (your contract amount)
2. Approved Change Order Nos. |  | (enter #) | (As per attached breakdown) (Net) |  |  | (Total change order amt.)
3. Adjusted Contract Amount | [5 empty] | (line 1 + 2)
4. Value of Work Completed to Date: (As per attached breakdown) | [5 empty] | (Amt completed to date)
5. Value of Approved Change Orders Completed: (As per attached breakdown) | [5 empty] | (Amt completed to date)
6. Materials Stored on Site: (As per attached breakdown) | [5 empty] | 0 |  | Info from Prior Period
7. Total to Date | [5 empty] | (Line 4 + 5) |  | Prior Total To Date: | Prior contract amount
8. Less Amount Retained |  | 10% | (or as stated in contract) |  |  | (Retainage per contract) |  | Prior Retainage | Prior retainage
9. Total Less Retainage | [5 empty] | (Line 7 - line 8) |  | Prior Previously Certified | total to date less ret.
10. Total Previously Certified (Deduct) | [5 empty] | (Amt. prev. billed)
11. AMOUNT DUE THIS REQUEST | [5 empty] | (line 9 - line 10)
CERTIFICATE OF THE SUBCONTRACTOR:
I hereby certify that the work performed and the materials supplied to date, as shown on the above represent the
actual value of accomplishment under the terms of the Contract (and all authorized changes thereto) between the
undersigned and |  |  |  | , relating to the above referenced project.
I also certify that payments, less applicable retention, have been made through the period covered by previous payments received from the contractor, to (1) all my subcontractors (sub-subcontractors) and (2) for all materials and labor used in or in connection with the performance of this Contract. I further certify I have complied with Federal, State and local tax laws, including Social Security laws and Unemployment Compensation laws and Workman’s Compensation laws insofar as applicable to the performance of this Contract.
Subscribed and sworn before me this ___________ day of
|  |  | , 20______ |  | Subcontractor
Notary Public:
[5 empty] | Authorized Signature |  | Date
My Commission Expires:
Title